## Sheet1
Project Start Date |  | 2026-01-01
Problem |  |  | Solution
Task | Depends On | Duration (Days) | Task | Earliest Start | Earliest Finish | Easy Sunday Excel Challenge
A |  | 4 | A | 2026-01-01 | 2026-01-04 | ⭐Calculate the earliest possible completion
B | A | 3 | B | 2026-01-05 | 2026-01-07 | date for every task.
C | B | 5 | C | 2026-01-08 | 2026-01-12 | ⭐Each task may only begin after its parent
D | B | 2 | D | 2026-01-08 | 2026-01-09 | task has finished.
E | C | 6 | E | 2026-01-13 | 2026-01-18 | ⭐Project Starts 1/1/2026
F | C | 4 | F | 2026-01-13 | 2026-01-16 | ⭐Solution MUST be dynamic
G | D | 5 | G | 2026-01-10 | 2026-01-14
H | D | 2 | H | 2026-01-10 | 2026-01-11
I | G | 3 | I | 2026-01-15 | 2026-01-17
J | G | 4 | J | 2026-01-15 | 2026-01-18
K |  | 7 | K | 2026-01-01 | 2026-01-07
L | J | 2 | L | 2026-01-19 | 2026-01-20